        ASSIGNMENT 6

1. How do you evaluate the performance of a project in agile?
We can evaluate the performance of a project in agile by measuring the following
- velocity
- hit rate
- work remaining on tasks
- project cost
Here the term velocity refers to the number of storypoints that can be taken in a sprint,if the velocity of the project is higher than than we expected then it means the project is on track.
Hit rate is defined as the percentage of work that was completed within the time allocated for doing that task.if the hit rate is low that means the project is not going according to the plan,also there will be delay in outcome of the project
Work remaining on tasks : if the task given to the project team was not completed, then the team will claculate the work remaining for completing the task.by this we can analyze the ability of the team and we can make a good plan according to the ability of the team
project cost : cost of the project must be tracked to ensure that the project does not go over budget

2. Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation

Sl No:	Traditional method	Agile method
1	It does not focus on Earned business value (EBV)	It focuses on Earned Business value. Business value is based on customer satisfaction
2	Project success based on Schedule Performance Index (SPI) and Cost Performance Index (CPI)	Project success based on Earned Business value / (EBV)
3	Schedule for the whole project is planned	Schedule is for each sprint.
4	Co-location is not necessary in this method.	Co-location is not necessary for the efficient delivery
5	Velocity is less . It takes more time to produce a working software.	Velocity is more. It takes less time to produce a working software as it is used in sprints.
6	Effort is calculated only at the last phase of the project.	Effort is calculated on each sprint
7	quality is measured in only one phase in the whole project life.	Quality is measured in each sprint life cylcle

3. With a total project budget of $ 175,000, and having completed one out of four Iterations, we have this product backlog and these actuals:

Feature	Estimate (storypoints)	Completed(storypoints)	Actual Cost(1000s / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

In our example, after Iteration 1 we should be at 25% complete)
- Calculate Planned Value
- Actual % Complete
- Earned Value
Answer:
planned Value =(25/100) * 175,000 = $ 43,750
Actual % Complete= (40/200)*100= 20%
Earned Value= (20/100)*175,000= $35,000